## Phase Overview
HRIS IMPLEMENTATION PLAN - MODULE BREAKDOWN BY PHASE
Municipality of Mariveles, Bataan • 20-Week Implementation Timeline
Phase | Duration | Modules | Key Deliverables | Start Date | End Date | Status | Critical Path
Phase 1 | 4 weeks | 6 modules | Core DB, Auth, Departments, Positions, Employees | Week 1 | Week 4 | Planning | Yes
Phase 2 | 6 weeks | 8 modules | Attendance, Leave, Payroll, Performance, Training | Week 5 | Week 10 | Planning | Yes
Phase 3 | 4 weeks | 5 modules | Analytics Views, Dashboards, KPIs, Reporting | Week 11 | Week 14 | Planning | Yes
Phase 4 | 6 weeks | 6 modules | AI Models, Chatbot, Anomaly Detection, UAT | Week 15 | Week 20 | Planning | Yes

## FOUNDATION
Module # | Module Name | Description | Key Tables | Endpoints | Effort | Dependencies | Technical Spec | Testing | Success Criteria
1 | 1.1 PostgreSQL Infrastructure | Deploy high-availability PostgreSQL cluster with replication, automated backups, monitoring | None (infrastructure) |  | 8 days | None | PostgreSQL 14+ with pg_partman Streaming replication (primary + 2 replicas) pg_stat_statements for query monitoring ... | Connection pool test (pgBouncer) Failover test (switch primary) Backup restore test (successful recovery) ... | Zero connection failures Recovery Time Objective (RTO) < 5 min ...
2 | 1.2 Core Schema & Audit Infrastructure | Create base schema with audit logs, change tracking, temporal tables | audit_logs, user_access_logs... | GET /api/audit-logs?table=X&record_id=Y | 5 days | 1.1 | audit_logs table (immutable, append-only) Trigger functions for auto-logging JSONB for old_values/new_values storage ... | INSERT trigger test UPDATE trigger test DELETE trigger test ... | All changes logged within 100ms Audit logs cannot be modified ...
3 | 1.3 Authentication & Authorization (RLS) | Implement role-based access control, database roles, row-level security policies | None (policy-based) |  | 6 days | 1.2 | 5 database roles: hr_admin, hr_write, hr_read, manager_read, employee_read PostgreSQL RLS policies per role Employees see only own records (policy: emp_id = current_user) ... | Employee role: can't view other employees Manager role: can view team data HR role: can view all, audit logged ... | Zero unauthorized data access All cross-role access logged ...
4 | 1.4 Departments & Positions Master Data | Create organizational structure with departments, positions, salary grades, reporting lines | departments, positions... | GET /api/departments GET /api/departments/{id}/children ... | 4 days | 1.3 | departments: hierarchical with parent_dept_id positions: salary_grade (SG-1 to SG-33), rank_classification Recursive CTE for org chart ... | Create 5-level department hierarchy Query org chart recursively Invalid salary grade rejection ... | Org chart loads <200ms Invalid data rejected ...
5 | 1.5 Employee Master Data Model | Create core employees table with all personal, employment, and contact info | employees, emergency_contacts | GET /api/employees GET /api/employees/{id} ... | 5 days | 1.4 | employees: 35+ columns (personal, employment, contact) PII fields: encrypted (gsis_number, sss_number, tin, pagibig) Soft delete: deleted_at timestamp ... | Create 1000 test employees Email uniqueness validation Encrypted field decryption ... | Employee lookup: <50ms Search (name/number): <100ms ...
6 | 1.6 Data Migration from Legacy System | Migrate employee data, positions, departments from legacy HR system, validate data quality | All Phase 1 tables | POST /api/admin/migration/validate | 7 days | 1.5 | ETL pipeline: legacy DB → staging → PostgreSQL Data mapping: legacy fields → new schema Validation rules: no NULL emp_number, valid email format, etc. ... | Sample data migration (100 employees) Data validation (completeness, uniqueness) Duplicate detection test ... | 100% data migration success Zero data loss ...

## OPERATIONS
Module # | Module Name | Description | Key Tables | Endpoints | Effort | Dependencies | Technical Spec | Testing | Success Criteria
1 | 2.1 Attendance Tracking System | Time tracking with biometric integration, clock-in/out, manual entry, WFH tracking | attendance, shift_schedules... | POST /api/attendance/clock-in POST /api/attendance/clock-out ... | 6 days | 1.5 | attendance: emp_id, date, time_in, time_out, status (Present/Late/Absent/Leave/WFH) Biometric integration: face recognition API hook Shift schedule support: different schedules per position ... | Clock-in within 30 sec Late detection: time_in at 9:31 AM (start 9:00) WFH mode: no time_in/out, status=WFH ... | Clock-in/out: <500ms response Late detection: 100% accuracy ...
2 | 2.2 Leave Management System | Leave request workflow, approval, balance tracking, CSC Form 6 compliance | leave_requests, leave_balances... | POST /api/leave-requests PUT /api/leave-requests/{id}/approve ... | 7 days | 1.5 | leave_requests: emp_id, leave_type, start_date, end_date, approval_status Leave types: Vacation, Sick, CTO, LWOP, Maternity, Paternity, Calamity, Bereavement Balance calc: opening_balance + days_earned - days_used - days_forfeited ... | Request 5-day vacation (approval flow) Sick leave: max 5 days without medical cert Balance calculation: 60-day annual allowance - 3 used = 57 remaining ... | Approval workflow: <2 sec per action Balance accuracy: 100% ...
3 | 2.3 Compensation & Salary Management | Salary grades, allowances, deductions, compensation history tracking | compensation, salary_grades... | GET /api/compensation/{emp_id} POST /api/compensation/{emp_id}/new-structure ... | 6 days | 1.4 | compensation: emp_id, effective_date, salary_grade, base_salary, allowances, deductions Allowances: PERA, meal, clothing (JSONB for flexibility) Deductions: GSIS, SSS, BIR, Pag-IBIG, loans (JSONB) ... | Create compensation structure: SG-1 to SG-33 Salary increase: update effective_date Allowance recalculation: PERA change ... | Salary calc accuracy: 100% (verified vs. manual) Effective dating: handles retroactive changes ...
4 | 2.4 Payroll Processing System | Monthly payroll runs, pay slip generation, budget variance tracking | payroll_runs, payroll_details... | POST /api/payroll/create-run PUT /api/payroll/{id}/process ... | 7 days | 2.3 | payroll_runs: payroll_period, pay_date, payroll_type (Monthly/13th/14th/Final) payroll_details: per-employee breakdown (gross, deductions, net) Status workflow: Draft → Processed → Approved → Posted ... | Create monthly payroll run (all employees) Process: calculate gross/net for 500 employees Approve: budget variance check (flag if >5%) ... | Payroll processing: <2 min for 500 employees Pay slip generation: <100ms per employee ...
5 | 2.5 Performance Management | Goal setting, progress tracking, performance reviews, ratings | performance_goals, performance_reviews... | POST /api/goals/{emp_id}/set PUT /api/goals/{id}/update-progress ... | 6 days | 1.5 | performance_goals: emp_id, fiscal_year, goal_description, target_metric, weight Goal status: Active, In Progress, Achieved, Not Achieved, Cancelled Reviews: emp_id, reviewer_id, fiscal_year, rating (1-5) ... | Set 3 goals per employee (weights: 0.4, 0.3, 0.3) Update goal progress quarterly Performance review: submit with rating ... | Goal tracking: real-time updates Achievement calc: accurate within 0.1% ...
6 | 2.6 Training & Development | Training catalog, enrollment, attendance tracking, certification management | training_catalog, training_enrollments... | GET /api/trainings POST /api/trainings/{id}/enroll/{emp_id} ... | 6 days | 1.5 | training_catalog: training_name, provider, hours, category, cost Enrollment: emp_id, training_id, enrollment_date, completion_date Attendance: training_id, emp_id, attendance_status (Present/Absent) ... | Create 50 training programs Enroll 100 employees in training Mark attendance: 95% present ... | Training catalog: <500ms load Enrollment: <1 sec per employee ...
7 | 2.7 Appointment History & Career Tracking | Track appointment changes, promotions, transfers, position history | appointment_history, promotion_history... | POST /api/appointments/{emp_id}/new POST /api/promotions/{emp_id}/create ... | 5 days | 1.5, 1.4 | appointment_history: emp_id, pos_id, appointment_date, start_date, end_date Promotion: from_pos_id, to_pos_id, promotion_date, salary_increase Transfer: from_dept_id, to_dept_id, transfer_date, transfer_reason ... | Record appointment: regular employee Promotion: SG-11 → SG-12 (with salary increase) Transfer: Finance → HR (same position) ... | Appointment recording: <2 sec Career timeline: <500ms load for 10-year history ...
8 | 2.8 Recruitment & Onboarding | Job postings, applicant tracking, offer management, onboarding checklists | job_postings, applicants... | POST /api/jobs/post GET /api/jobs ... | 7 days | 1.4, 1.5 | job_postings: pos_id, posting_date, closing_date, posting_status applicants: first_name, email, resume, application_status, qualifications_met Offers: applicant_id, position_id, salary_offer, offer_date, acceptance_status ... | Post 5 job openings Receive 50 applications Screen & shortlist: 10 candidates ... | Job posting: <3 sec Application submission: <5 sec ...

## ANALYTICS
Module # | Module Name | Description | Key Tables | Endpoints | Effort | Dependencies | Technical Spec | Testing | Success Criteria
1 | 3.1 Materialized Views & Data Warehouse Prep | Create 7 materialized views for fast dashboard queries, refresh strategy | mv_workforce_demographics, mv_attendance_metrics... | GET /api/analytics/dashboard-data | 5 days | All Phase 2 modules | Materialized views: refresh hourly (off-peak hours) Partitioning by date for large views Compression: enable for historical partitions ... | Create view: mv_workforce_demographics Refresh cycle: 1 hour Data accuracy: sample check vs. source ... | View refresh: <5 min each Dashboard query: <500ms ...
2 | 3.2 Real-Time Dashboard Queries | Optimized SQL queries for executive, manager, HR, and payroll dashboards | All Phase 2 tables + materialized views | GET /api/dashboards/executive GET /api/dashboards/manager/{emp_id} ... | 5 days | 3.1 | Query optimization: use materialized views, indexed CTEs Caching: Redis for frequently-accessed metrics (30-min TTL) Pagination: support 100+ metrics per dashboard ... | Executive dashboard load: <1 sec Manager view team metrics: <500ms HR analytics: 20 metrics in <2 sec ... | Dashboard load: <1 sec Metric filter: <300ms ...
3 | 3.3 KPI Tracking & Alerts | 20+ KPIs with automated calculation, trend analysis, alert thresholds | kpi_values, kpi_thresholds... | GET /api/kpis GET /api/kpis/{kpi_id}/trend?months=12 ... | 5 days | 3.1 | KPI calculation: scheduled job (daily, weekly, monthly) Thresholds: red/yellow/green ranges per KPI Alerts: auto-generated when threshold breached ... | Calculate 20 KPIs daily Attendance rate threshold: alert if <90% Turnover rate: alert if >15% quarterly ... | KPI calculation: <2 min for all 20 Alert generation: real-time (<5 min) ...
4 | 3.4 Workforce Demographics & Analytics | Gender, age, tenure distributions, salary analysis, diversity metrics | All Phase 2 tables | GET /api/analytics/demographics GET /api/analytics/salary-analysis?salary_grade=SG-15 ... | 4 days | 3.1, 3.2 | Demographics: headcount by gender, age bracket (20-29, 30-39, etc.) Salary: avg/median/range by grade, department Tenure: distribution (0-1yr, 1-3yr, 3-5yr, 5-10yr, 10+yr) ... | Gender breakdown: 500 employees (verify count) Age distribution: 10 brackets Salary range: min/max/avg by SG ... | Demographics load: <500ms Salary analysis: <1 sec ...
5 | 3.5 Recruitment & Turnover Analytics | Recruitment pipeline, time-to-hire, turnover analysis, retention trends | All Phase 2 tables + applicants | GET /api/analytics/recruitment-pipeline GET /api/analytics/time-to-hire ... | 5 days | 3.1, 3.2 | Pipeline: funnel view (applied → shortlisted → offered → hired) Time-to-hire: avg days from posting to start date Turnover: separations by reason (resignation, retirement, termination) ... | Pipeline funnel: 100 applicants → 10 hired Time-to-hire: calc avg 45 days Turnover by reason: resignations, retirements breakdown ... | Pipeline load: <1 sec Time-to-hire accuracy: ±1 day ...

## AI & ADVANCED
Module # | Module Name | Description | Key Tables | Endpoints | Effort | Dependencies | Technical Spec | Testing | Success Criteria
1 | 4.1 Retention Risk Scoring Model | ML model (Random Forest/Logistic Regression) to predict flight-risk employees | ml_retention_scores, ml_model_versions | GET /api/ml/retention-risk GET /api/ml/retention-risk/{emp_id} ... | 8 days | 3.4, 3.5 | Features: tenure, dept, promotions/2yr, training_hours/yr, perf_rating_trend, leave_spike, salary_vs_market Target: left_within_12mo (binary classification) Algorithm: Random Forest (non-linear relationships) ... | Train on 3-year historical (300+ separations) Validate: precision >80%, recall >75% Test on recent employees (known outcomes) ... | Model accuracy: >80% precision Recall: >75% (catch real risks) ...
2 | 4.2 Skill Gap Identification | Match employee training/certifications to position requirements, recommend training | skill_requirements, employee_skills... | GET /api/ml/skill-gaps/{emp_id} GET /api/ml/training-recommendations/{emp_id} ... | 6 days | 2.6, 3.1 | Position requirements: define 5-10 critical skills per role Employee skills: map training_records → skill competency Gap detection: skill_required ∉ employee_skills ... | Define skill requirements: Finance position requires Excel/SAP Employee has Excel (training_record), missing SAP Gap detection: SAP recommended (training course X) ... | Gap identification: 100% of gaps detected Recommendation accuracy: relevant to position ...
3 | 4.3 Succession Planning & High-Potential Identification | Identify internal talent ready for leadership roles, succession readiness | ml_succession_candidates, readiness_assessments | GET /api/ml/succession-plan?position_id=X GET /api/ml/high-potential ... | 7 days | 2.5, 3.4, 4.1 | Features: perf_rating (top quartile), promotions (2+ in 5yr), training (leadership cert), tenure, age Readiness levels: Ready Now (0-6mo), Soon (6-12mo), Development (1-2yr) Risk: high-performer + approaching-retirement = succession risk ... | Identify high-performers: top 25% by rating Leadership training check: completed program Succession ranking: Jane (ready now), Bob (ready soon), Alice (development) ... | Succession readiness: 100% of critical positions identified Ranking accuracy: validated by HR team ...
4 | 4.4 Chatbot / AI Assistant Backend | Natural language interface for employee self-service questions (leave balance, salary, etc.) | chatbot_queries, chatbot_responses | POST /api/chatbot/ask GET /api/chatbot/faq ... | 8 days | All Phase 2 modules | NLP: extract intent (ask_leave_balance, request_leave, etc.) Database queries: safely execute queries based on intent Privacy: mask sensitive data (salary, SSN) based on role ... | Q: 'How many vacation days do I have left?' → Query leave_balance, return 15 days Q: 'What's my current salary?' → Mask sensitive digits, return range Q: 'How do I request leave?' → Return guided workflow with link ... | Intent accuracy: >85% recognition Response time: <2 sec ...
5 | 4.5 Anomaly Detection Pipeline | Detect unusual HR/payroll patterns, compliance alerts | anomalies_detected, anomaly_alerts | GET /api/ml/anomalies GET /api/ml/anomalies/{type}?severity=High | 6 days | 2.1, 2.2, 2.3, 3.1 | Patterns: high overtime spike, sudden leave requests, unusual salary changes, access anomalies Detection: statistical thresholds (>3σ deviation) + ML-based Alert: real-time notification to HR/Compliance ... | Overtime spike: Dept A avg 10 OT hours/mo → 40 hours this mo (flagged) Sick leave spike: Employee used 0 sick days, then 5 in one week (flagged) Salary change: salary raised 20% vs. historical 2% annual raises (flagged) ... | Detection latency: <10 min after anomaly occurs False positive rate: <5% ...
6 | 4.6 Workload Forecasting & Staffing Plan | Predict 6-12 month staffing needs based on turnover, growth, retirement | ml_staffing_forecast | GET /api/ml/staffing-forecast?horizon=12mo GET /api/ml/recruitment-plan | 7 days | 3.5, 4.1 | Inputs: historical turnover by dept/position, retirement eligibility, growth plans, seasonal patterns Model: time-series forecasting (ARIMA or Prophet) Output: staffing needs by position, month ... | Historical data: 3-year turnover patterns Forecast: predict next 12 months staffing needs Validation: compare forecast vs. actual (post-implementation) ... | Forecast accuracy: MAPE <15% Plan actionability: HR can execute within 2 weeks ...
7 | 4.7 User Acceptance Testing (UAT) & Training | Comprehensive UAT, staff training, go-live readiness | N/A | N/A | 8 days | All Phase 4 modules | UAT scenarios: 50+ test cases covering all workflows Environments: staging (prod-like), UAT (user-facing) Sign-off: HR leads approve each function ... | Employee onboarding scenario: end-to-end Leave request approval workflow Payroll processing: draft to post ... | UAT pass rate: 100% (zero blockers) Training completion: 95% of staff trained ...
8 | 4.8 Go-Live & Post-Launch Support | Production launch, day-1 monitoring, support, issue resolution | N/A | N/A | 6 days (ongoing) | 4.7 | Cutover plan: data migration, system switch, legacy system shutdown Monitoring: 24/7 during first week (SLA: <1hr response time) Rollback plan: if critical issues, revert to legacy ... | Pre-go-live: final data validation Cutover execution: switch users from legacy to new system Day-1 monitoring: check dashboard health, report performance ... | System uptime: >99.9% (no more than 45 min downtime/month) Performance: all dashboards <1 sec load ...