## Summary
HCM360 HRIS — LGU Gap Analysis
Municipality of Mariveles, Province of Bataan — Human Resource Management Office
As Of April 22, 2026 · HCM360 v1.0.0
Coverage Summary
Status | Count | % of Total | Meaning
COVERED |  |  | Fully implemented — production-ready for LGU use
PARTIAL |  |  | Exists; requires LGU-specific tuning, templates, or configuration
GAP |  |  | Needs new development before deployment
TOTAL |  | 100% | Requirements mapped from LGU document
Critical Gaps — Top Priorities for LGU Deployment
• CS Form No. 6 (revised 2020) — leave application strict compliance
• CS Form No. 7 (s.2017) — Exit Interview
• Personal Data Sheet (PDS) — CSC-prescribed template with versioning
• IPCR / OPCR performance contract templates
• Travel Order + Locator Slip modules (pre-approval + DTR integration)
• Face-recognition + mobile geo-tagged check-in (flag raising/lowering)
• Step Increment tracking (every 3 years from Date of Original Appointment)
• Retirement monitoring (Age 60 early / 65 mandatory) + multi-recipient notice
• Job Order / LSB / BHW / Nutritionist Scholar contract workflows
• CSC Eligibility reporting split by 1st Level vs 2nd Level by gender

## Full Matrix
Section | Requirement | Status | HCM360 Module | Page / Route | Gap / Notes | Priority
1. CSC PRIME-HRM Level 2 | Recruitment, Selection, Placement (RSP) | COVERED | Recruitment | /recruitment | Requisitions, candidates, CSC eligibilities, qualification standards | Low
1. CSC PRIME-HRM Level 2 | Performance Management (PM) | COVERED | Performance Management | /performance | Review cycles, KPIs, competency-based evaluation | Low
1. CSC PRIME-HRM Level 2 | Learning and Development (L&D) | COVERED | Learning & Development | /learning | Training catalog, enrollments, certifications | Low
1. CSC PRIME-HRM Level 2 | Rewards and Recognition (R&R) | COVERED | Rewards & Recognition | /rewards | Awards, praise wall, nominations | Low
1. CSC PRIME-HRM Level 2 | CSC PRIME-HRM Level 2 certification alignment | PARTIAL | All four modules | /admin/reference | Modules present; formal CSC audit alignment pending | High
2. Report Generating (Functional) | Data sources — pull from multiple DBs/systems | COVERED | Services | services/db.py + reporting_service | Centralized psycopg2 pool with view-based aggregation | Low
2. Report Generating (Functional) | Report design (drag-drop / designer) | PARTIAL | Analytics | /reports (report builder) | Saved queries + parameters; drag-drop UI would enhance | Medium
2. Report Generating (Functional) | Data analysis (query, analyze, summarize) | COVERED | Analytics | /reports/demographics, /reports | Materialized views + SQL-driven metrics | Low
2. Report Generating (Functional) | Manual + automated report generation | COVERED | Analytics + Reminders | /admin/reminders, /reports | Reminder rules can trigger scheduled reports | Low
2. Report Generating (Functional) | Output: screen, PDF, spreadsheet, print | COVERED | Reporting Service | services/reporting_service.py | PDF via ReportLab; CSV/Excel export available | Low
2. Report Generating (Functional) | Output: email distribution | PARTIAL | Reminders | /admin/reminders | Reminder engine exists; SMTP config must be wired in .env | Medium
2. Report Generating (Functional) | Security — authentication & authorization | COVERED | Access Service | /admin/access-matrix | 3-tier RBAC (page, feature, modification) | Low
2. Report Generating (Non-Functional) | Performance (speed, load response) | COVERED | Infrastructure | docker-compose.yml | PG tuned (shared_buffers 256MB, max_connections 200) | Low
2. Report Generating (Non-Functional) | Scalability (data volume, user growth) | COVERED | Infrastructure | docker-compose.yml | Stateless web tier, pool-based DB access, volume-backed | Low
2. Report Generating (Non-Functional) | Reliability (error handling, integrity, audit) | COVERED | Audit Logs | audit_logs schema | Trigger-based change capture on all mutations | Low
3. Attendance Monitoring | Online leave application & approval | COVERED | Leave Management | /leave/requests, /me/leaves | Full workflow: PENDING → APPROVED → balance debit | Low
3. Attendance Monitoring | Compensatory Time Off (CTO) workflow | PARTIAL | Leave Management | /leave/types | Add CTO to lv_types with accrual rules tied to OT | Medium
3. Attendance Monitoring | Travel Order — online application & pre-approval | GAP | New module | /travel-orders (to build) | Needs new blueprint: request, routing, DTR integration | High
3. Attendance Monitoring | Request for Training / Office Order | PARTIAL | L&D + Workflow | /learning/enrollments | Enrollments exist; office-order form template needed | Medium
3. Attendance Monitoring | Locator Slip with pre-approval | GAP | New module | /locator-slips (to build) | Needs new blueprint tied to DTR | High
3. Attendance Monitoring | Pre-approved items auto-reflect on DTR + invalidate overlaps | COVERED | Attendance | /attendance/daily | Leave requests already block DTR-day conflicts | Low
3. Attendance Monitoring | Mobile / desktop time-tracking with OT + remote check-in | PARTIAL | Attendance | /me/attendance | Web time-in/out exists; native mobile + remote check-in need build | High
3. Attendance Monitoring | Online DTR check, acknowledge, approve | COVERED | Attendance | /attendance/daily, /me/attendance | Approval workflow wired to supervisor | Low
3. Attendance Monitoring | Civil Service Form No. 6 (revised 2020) — strict implementation | GAP | Leave Management | /leave/requests/new (CS6 mode) | CS Form No. 6 template + exact fields + strict routing | High
3. Attendance Monitoring | Travel Order + Locator Slip pre-approval & monitoring | GAP | New module | /travel-orders, /locator-slips | Workflow engine exists; forms not yet modelled | High
3. Attendance Monitoring | Monitor habitual tardiness & AWOL | COVERED | Attendance | /attendance/alerts | att_alerts generates alerts on thresholds | Low
3. Attendance Monitoring | Auto-alert when VL < 5 days or tardiness reaches 7x | PARTIAL | Reminders | /admin/reminders | Threshold rules configurable; specific LGU thresholds to be seeded | Medium
3. Attendance Monitoring | Face-recognition attendance / automated record | GAP | Attendance | N/A | Hardware + facial API integration (e.g., AWS Rekognition) | High
3. Attendance Monitoring | Shift schedule mgmt (security, rescue, medical, on-call) | COVERED | Attendance | /attendance/shifts, /attendance/shift-assignments | Shift types + per-employee assignments | Low
3. Attendance Monitoring | Flag raising / lowering mobile check-in with photo | GAP | Attendance + Mobile | mobile app (to build) | Requires mobile client + photo upload + geotag | High
4. Recruitment | Auto-notify qualified next-in-rank of posted vacancy | PARTIAL | Recruitment + Reminders | /recruitment/requisitions | Requisition posting exists; next-in-rank ranking rule needs logic | Medium
4. Recruitment | Pre-assess online applications vs CSC qualification standards | COVERED | Recruitment | /recruitment/candidates | rsp.qualification_standards + rsp.csc_eligibilities | Low
4. Recruitment | Retain applications for 5 years | PARTIAL | DMS + Retention | /admin/reference-data/retention_policies | Set retention policy to 5 years for recruitment docs | Medium
4. Recruitment | Source candidates — internal/external + 3 conspicuous places + job portals | PARTIAL | Recruitment | /recruitment/requisitions | Internal + external tracked; job-portal API integration additional | Medium
4. Recruitment | Online approval — JO, LSB, Barangay Health Worker/Nutritionist Scholar contracts | GAP | Recruitment | /recruitment/contracts (to build) | LGU-specific contract types and approval chains required | High
4.1 Onboarding / Offboarding | Digital onboarding — forms, checklists, policy ack, equipment, training | COVERED | Onboarding | /me/onboarding | Checklist with stages (ACTIVATED, etc.) | Low
4.1 Onboarding / Offboarding | Electronic signature on documents | GAP | DMS | /dms (needs e-sig module) | Integrate DocuSign / local PKI provider | High
4.1 Onboarding / Offboarding | Offboarding — exit interview, CS Form No. 7, transition, asset return, access removal, archive | PARTIAL | ESS + DMS + Admin | /me/offboarding, /admin/users | Stages exist; CS Form No.7 template + auto-deactivate on last day | High
5. Performance Management | Goal-setting & progress tracking for employees, dept heads, PM team | COVERED | Performance Management | /performance/goals | KPIs + competencies per cycle | Low
5. Performance Management | IPCR & OPCR periodic review | PARTIAL | Performance Management | /performance/reviews | Review engine exists; IPCR/OPCR CSC templates to be added | High
5. Performance Management | Succession planning — critical roles + internal candidates | PARTIAL | Performance + Workforce Planning | /workforce-planning, /performance | Scenarios exist; succession slate UI needs dedicated page | Medium
6. Learning and Development | Post available trainings/seminars; track needs | COVERED | L&D | /learning/catalog, /learning/enrollments | Catalog with prerequisites, needs-based flagging | Low
6. Learning and Development | Training attendance via mobile with geotag + AM/PM + date | GAP | L&D + Mobile | /learning/attendance (mobile) | Requires mobile client with GPS + timestamped photo | High
6. Learning and Development | Online Narrative Report Form before acknowledgment | GAP | L&D | /learning/narrative-report (to build) | New form module tied to enrollment completion | Medium
7.1 Loyalty Service Award | Auto-identify employees reaching 10 years continuous service | PARTIAL | R&R | /rewards/awards | Date_hired tracked; milestone-detection job needs seeding | Medium
7.1 Loyalty Service Award | Every 5 years thereafter (15, 20, 25, 30, …) | PARTIAL | R&R | /rewards/awards | Add recurring-milestone logic in rr_service | Medium
7.1 Loyalty Service Award | Auto Notice / Memo generation for loyalty award | GAP | R&R + DMS | /dms/certificate-types | Add certificate template "Loyalty Award Memo" with auto-populate | Medium
7.2 Step Increment | Auto-track Step Increment eligibility every 3 years | GAP | Core HR + Payroll | /employees (step-increment tab) | Add step_increment_history table + scheduled job | High
7.2 Step Increment | Based on Date of Original Appointment | PARTIAL | Core HR | core.employees.date_hired | Add date_of_original_appointment field (separate from date_hired) | High
7.2 Step Increment | Generate Step Increment Due Report | GAP | Analytics | /reports (new report) | Build report tied to new step_increment_history | Medium
7.2 Step Increment | Generate Step Increment Notice / Memo | GAP | DMS | /dms/certificate-types | Certificate template "Step Increment Notice" | Medium
7.3 Retirement Monitoring | Auto-identify approaching retirement with gender breakdown | PARTIAL | Core HR + Analytics | /reports/demographics | date_of_birth exists; retirement-age config + gender split report | High
7.3 Retirement Monitoring | Early Retirement Age 60 / Mandatory 65 | GAP | Core HR | /admin/reference-data/retirement_rules | Add retirement_rules reference table | High
7.3 Retirement Monitoring | List of nearing retirement (6 months / 1 year before) | GAP | Analytics | /reports/retirement-due | New report based on age + retirement rules | High
7.3 Retirement Monitoring | Retirement Notice / Memo for HR, Employee, Accounting/Budget/Payroll | GAP | DMS + Workflow | /dms/certificate-types + /workflow | Multi-recipient certificate + routing | High
7.3 Retirement Monitoring | Male/Female breakdown for Age 60+ and 65+ | COVERED | Analytics | /reports/demographics | Demographics report has gender; extend filter for retirement eligibility | Low
8. Payroll System | Payroll automation — salaries, deductions by role/hours | COVERED | Payroll | /payroll/runs | DRAFT → COMPUTING → COMPUTED → APPROVED → POSTED | Low
8. Payroll System | Generate digital payslips | COVERED | Payroll | /payroll/payslips/<id>/pdf, /me/payslips | On-demand PDF via reporting_service | Low
8. Payroll System | Benefits administration portal (integrated with payroll) | COVERED | ESS + Payroll | /me/benefits | Enrollment + employer/employee cost tracking | Low
8. Payroll System | Encode GSIS, Pag-IBIG, Coop, Cash Advance loans | COVERED | Payroll | /payroll/loans | pay_loans with loan_type enum covering all LGU sources | Low
8. Payroll System | Loan details — amount, terms, start date, end date | COVERED | Payroll | /payroll/loans | Standard fields on pay_loans | Low
8. Payroll System | Monthly payment & outstanding balance (manual input) | COVERED | Payroll | /payroll/loans | Amortization schedule + manual override | Low
8. Payroll System | View Employee Loan Profile per personnel | COVERED | ESS | /me/compensation | Active loans shown on compensation page | Low
8. Payroll System | Generate Loan Summary List | COVERED | Payroll | /payroll/loans (export) | CSV/Excel export available | Low
9. Security & Data Governance | Role-based permissions (HR, MIS, employees) | COVERED | Access Service | /admin/access-matrix | 3-tier: page / feature / modification | Low
9. Security & Data Governance | Audit trails — who edited what, when; access logs | COVERED | Audit Logs | audit_logs.change_log, audit_logs.access_log | Trigger-based capture | Low
9. Security & Data Governance | Data encryption in transit & at rest + backups / DR | PARTIAL | Infrastructure | docker-compose.yml + TLS proxy | TLS at reverse proxy; host disk encryption; DR via pg_dump backups/ | High
9. Security & Data Governance | Compliance modules — labor laws, tax, data privacy | COVERED | Privacy + Payroll | /admin/privacy, /payroll | RA 10173 field-level privacy; BIR/SSS/PhilHealth/HDMF schedules | Low
9. Security & Data Governance | Archival & retention — auto removal/archiving of old records | PARTIAL | DMS | /admin/reference-data/retention_policies | Policies exist; scheduled archival job to be built | Medium
10. Employee Records Management | Central searchable employee profile | COVERED | Core HR | /employees, /employees/<id> | 201 file with sub-records; global search at /search | Low
10. Employee Records Management | Digital document storage with version control & expiry | COVERED | DMS | /dms, /employees/<id>/documents | document_categories + expiration + retention | Low
10. Employee Records Management | Role / position management; live org chart | COVERED | Core HR + Orgchart | /orgchart, /admin/reference-data/positions | Positions + departments + org chart | Low
10. Employee Records Management | Full lifecycle — recruitment → onboarding → active → transitions → offboarding | COVERED | Multiple | /recruitment, /me/onboarding, /employees, /me/offboarding | End-to-end coverage | Low
10. Employee Records Management | Paperless records with e-signatures, version control, audit | PARTIAL | DMS | /dms | Paperless + audit exists; e-signature integration pending | High
10. Employee Records Management | Employee Masterfile (Personal & Employment) | COVERED | Core HR | /employees/<id> | v_employees_full view exposes everything | Low
10. Employee Records Management | Personal Data Sheet (PDS) storage — CSC template | GAP | DMS + Core HR | /employees/<id>/pds (to build) | Build PDS form following CSC template; auto-fill from masterfile | High
10. Employee Records Management | Service Records & Appointment History | PARTIAL | Core HR | /employees/<id>/service-record | Transitions tracked; formal CSC Service Record export pending | High
10.1 HR Demographics (M/F breakdown) | Gender Profile — total M/F overall + by dept/office | COVERED | Analytics | /reports/demographics | Demographics dashboard with department split | Low
10.1 HR Demographics (M/F breakdown) | Age Profile — distribution by gender | COVERED | Analytics | /reports/demographics | Age-bucket histogram with gender | Low
10.1 HR Demographics (M/F breakdown) | Status of Appointment — Permanent/Casual/Contractual/JO/COS by sex | PARTIAL | Core HR + Analytics | /admin/reference-data/employment_types | Add JO and COS as employment types; extend report | Medium
10.1 HR Demographics (M/F breakdown) | Rank Classification — Rank-and-File vs Officer/Supervisory M/F | PARTIAL | Core HR | core.positions | Add rank_classification column to core.positions; feed report | Medium
10.1 HR Demographics (M/F breakdown) | Educational Attainment by gender (Graduate/College/HS/Elementary) | PARTIAL | Core HR | core.employees.education_level | Field exists; CSC-specific buckets and reporting to add | Medium
10.1 HR Demographics (M/F breakdown) | Eligibility Profile — 1st Level / 2nd Level by gender | GAP | Core HR + RSP | rsp.csc_eligibilities | Add 1st/2nd level classification + demographic report | High
10.1 HR Demographics (M/F breakdown) | Plantilla Summary — filled vs vacant by gender | PARTIAL | Workforce Planning | /workforce-planning | Current vs. planned shown; plantilla report needs gender split | Medium
10.1 HR Demographics (M/F breakdown) | Salary Grade Distribution — count per grade with M/F | COVERED | Analytics | /reports/demographics | Salary grade × gender matrix | Low
10.1 HR Demographics (M/F breakdown) | Training history per employee + summary with gender breakout | COVERED | L&D + Analytics | /reports/training, /learning/attendance | Enrollment & completion data | Low
11. Reporting, Analytics & Dashboards | Real-time dashboards (headcount, turnover, absence, leave trends) | COVERED | Analytics | / (main), /reports | dashboard_metrics drives role-filtered KPI cards | Low
11. Reporting, Analytics & Dashboards | Pre-built & custom reports; CSV/Excel export | COVERED | Analytics | /reports | Saved queries + parameters; export utilities | Low
11. Reporting, Analytics & Dashboards | Predictive analytics — retention risk, workforce forecast | PARTIAL | AI + Workforce Planning | /ai, /workforce-planning | Scenarios + AI assistant exist; explicit attrition scoring model pending | Medium
12. Self-Service & Mobile | All functions accessible on mobile | PARTIAL | UI | All /me/* pages | Responsive web; native mobile app to enhance | High
12. Self-Service & Mobile | Employee self-service portal | COVERED | ESS | /me, /me/profile, /me/leaves, /me/payslips | Full self-service suite | Low
12. Self-Service & Mobile | Dept head self-service — approve leaves, dashboards, team reports | COVERED | MSS | /team, /team/approvals, /me/inbox | Manager service ready | Low
12. Self-Service & Mobile | Online Request — COE, Service Record, SALN PDF, Appointment PDF | PARTIAL | DMS | /me/certificates | COE & Service Record present; SALN and Appointment templates pending | High
13. Modern / Futuristic Add-Ons | Chatbot / self-help assistant | PARTIAL | AI | /ai | ARIA AI exists; conversational chatbot UI to be enhanced | Medium
13. Modern / Futuristic Add-Ons | AI-driven insights — skill gap, training, attrition risk | PARTIAL | AI + Workforce Planning | /ai, /workforce-planning | Skill gap built in; attrition scoring model to add | Medium
13. Modern / Futuristic Add-Ons | Flexible work — hybrid/remote, geolocation clock-in, virtual check-in | GAP | Attendance | mobile app (to build) | Work arrangement tracked; geolocation clock-in requires mobile | High
13. Modern / Futuristic Add-Ons | Digital org chart — drag-drop, reporting lines, vacancies live | PARTIAL | Orgchart | /orgchart | Tree visualization + privacy; drag-drop editing pending | Medium
14. Integration & Ecosystem | API / connectors — payroll, ERP/finance, SSO, time-clock | PARTIAL | Multiple | payroll_web service, SSO JWT flow | Payroll microservice + JWT SSO; formal REST API + ERP/biometric connectors to document | Medium
14. Integration & Ecosystem | Data import/export — migration, bulk updates | COVERED | Admin | /admin/reference, /admin/demo-data | CSV import tools + Demo Data profiles | Low

## Gap Backlog
Gap Backlog — Items to Build for LGU Deployment
ID | Requirement | Target Module | Target Page / Route | Effort Size | Estimate | Priority
G01 | CS Form No. 6 leave application template & strict workflow | Leave Management | /leave/requests/new (CS6 mode) | Medium | 2 weeks | High
G02 | CS Form No. 7 Exit Interview template | Offboarding + DMS | /me/offboarding/cs7 | Small | 1 week | High
G03 | Travel Order module with pre-approval + DTR integration | New module | /travel-orders | Medium | 3 weeks | High
G04 | Locator Slip module with pre-approval | New module | /locator-slips | Small | 2 weeks | High
G05 | Face-recognition attendance integration | Attendance + 3rd-party | mobile app + face-match API | Large | 6 weeks | High
G06 | Mobile flag-raising/lowering check-in with photo + geotag | Attendance + Mobile | mobile app | Large | 6 weeks | High
G07 | Job Order / LSB / BHW / Nutritionist Scholar contracts | Recruitment | /recruitment/contracts | Medium | 3 weeks | High
G08 | Electronic signature on documents | DMS | /dms (e-sig integration) | Medium | 2 weeks | High
G09 | Mobile training attendance with geotag + AM/PM | L&D + Mobile | mobile app | Medium | 3 weeks | High
G10 | Training Narrative Report Form | L&D | /learning/narrative-report | Small | 1 week | Medium
G11 | Loyalty Award auto-memo generator | R&R + DMS | /dms/certificate-types (Loyalty) | Small | 1 week | Medium
G12 | Step Increment tracking & notice | Core HR + Payroll | /employees/<id>/step-increment | Medium | 2 weeks | High
G13 | Retirement monitoring & multi-recipient notice | Core HR + Workflow | /reports/retirement-due, /workflow | Medium | 2 weeks | High
G14 | Personal Data Sheet (PDS) — CSC template | Core HR + DMS | /employees/<id>/pds | Medium | 3 weeks | High
G15 | CSC Eligibility 1st/2nd Level reporting | Core HR + Analytics | /reports/eligibility | Small | 1 week | High
G16 | SALN PDF generation | DMS | /me/certificates (SALN template) | Medium | 2 weeks | High
G17 | Appointment PDF generation | DMS | /me/certificates (Appointment template) | Small | 1 week | High
G18 | Attrition risk scoring model | AI + Analytics | /ai/insights | Medium | 3 weeks | Medium
Totals |  |  |  | Small: 6 / Medium: 10 / Large: 2 |  | High: 15 / Med: 3

## Partial Refinements
Partial Refinements — Configuration & Minor Build Tasks
ID | Refinement | Target Module | Action
P01 | Seed CTO as leave type | Leave | Admin → Reference → lv_types → add CTO with OT accrual
P02 | IPCR / OPCR templates | PM | Add templates to performance review cycles
P03 | Job Portal posting integration | RSP | Add posting webhooks to 3rd-party job portals
P04 | Successor slate UI | PM | New tab on /performance showing critical roles + slate
P05 | CSC-specific employment types (JO, COS) | Core HR | Reference → employment_types → add JO, COS
P06 | Rank classification on positions | Core HR | Add rank_classification column to core.positions
P07 | Education bucket config per CSC | Core HR | Normalize education_level values; add report buckets
P08 | Plantilla Summary by gender | Workforce Planning | Extend existing scenario report with gender split
P09 | Next-in-rank auto notification on vacancy | RSP + Reminders | Add rank-based rule to reminder engine
P10 | Retention policy: 5 years for recruitment docs | DMS | Set retention_policies for Recruitment category
P11 | SMTP email delivery for reports/reminders | Reminders | Configure SMTP_HOST, SMTP_USER, SMTP_PASS in .env
P12 | Disk encryption + TLS proxy | Infrastructure | Deploy behind nginx/Caddy with LE certs; LUKS on host
P13 | Scheduled archival of off-boarded employees | DMS | Cron job for retention_policies execution
P14 | Drag-drop report builder UI | Analytics | Upgrade /reports with drag-drop canvas
P15 | Chatbot conversational UI | AI | Wrap existing AI endpoints with chat UI
P16 | Drag-drop org chart editing | Orgchart | Enable node-drop reassignment on /orgchart
P17 | Next-of-kin/rank notification for vacancies | RSP | Configure reminder rule
P18 | Mobile responsive enhancements | UI | Audit each /me page for <640px viewports
P19 | COE and Service Record HTML-to-PDF templates | DMS | Add CSC-aligned certificate templates
P20 | Retirement rules seeding (60 early, 65 mandatory) | Core HR | New reference table + age check on demographics

## Module Coverage
Coverage by HCM360 Module
Module | COVERED | PARTIAL | GAP | Total | Coverage %
Core HR
Attendance
Leave Management
Payroll
Recruitment
Performance Management
Learning & Development
Rewards & Recognition
DMS
Workforce Planning
Analytics
ESS
MSS
AI
Orgchart
Access Service
Audit Logs
Infrastructure
Reminders
Privacy
New module
Services
Onboarding
Reporting Service
Admin
UI
ALL MODULES

## Roadmap
Recommended Phasing for LGU Deployment
Phase | Timeline | Theme | Deliverable
Phase 1 | Weeks 1-4 | LGU Readiness Baseline | Configure reference data (CTO, JO, COS, rank classification, retention policies)
Phase 1 | Weeks 1-4 | LGU Readiness Baseline | Wire SMTP for reminders and report delivery
Phase 1 | Weeks 1-4 | LGU Readiness Baseline | Deploy behind TLS reverse proxy with production SECRET_KEY rotation
Phase 1 | Weeks 1-4 | LGU Readiness Baseline | Seed LGU-specific departments, positions, plantilla
Phase 1 | Weeks 1-4 | LGU Readiness Baseline | Train HR administrators on access matrix and privacy rules
Phase 2 | Weeks 5-10 | Critical CSC Forms | CS Form No. 6 leave application (strict)
Phase 2 | Weeks 5-10 | Critical CSC Forms | CS Form No. 7 exit interview
Phase 2 | Weeks 5-10 | Critical CSC Forms | Personal Data Sheet (PDS) with auto-fill
Phase 2 | Weeks 5-10 | Critical CSC Forms | IPCR / OPCR templates for performance reviews
Phase 2 | Weeks 5-10 | Critical CSC Forms | Travel Order + Locator Slip modules
Phase 2 | Weeks 5-10 | Critical CSC Forms | Loyalty Award, Step Increment, Retirement notice workflows
Phase 3 | Weeks 11-16 | Mobile & Biometrics | Native mobile app (Flutter / React Native) for employees
Phase 3 | Weeks 11-16 | Mobile & Biometrics | Geolocation + photo check-in (flag raising/lowering, training)
Phase 3 | Weeks 11-16 | Mobile & Biometrics | Face-recognition biometric attendance integration
Phase 3 | Weeks 11-16 | Mobile & Biometrics | Electronic signature integration (DocuSign or local PKI)
Phase 4 | Weeks 17-20 | Intelligence | Attrition risk scoring model
Phase 4 | Weeks 17-20 | Intelligence | Chatbot conversational UI
Phase 4 | Weeks 17-20 | Intelligence | Drag-drop report builder
Phase 4 | Weeks 17-20 | Intelligence | Drag-drop org-chart editor with vacancy overlay